## Bug Tracker
Bug ID | Environment | Feature / Module | Defect Description & Steps to Reproduce | Severity | Priority | Reporter | Assigned Dev | Status | Target Fix Date | Retest Date | Build / Release Version
BUG-001 | Dev / Local | GPU Job Queue | Jobs ran strictly one at a time in upload order, so alternating English/Tamil uploads swapped engines on every job and nothing ran in parallel. Steps: 1. Upload 4 papers in the order Eng, Tam, Eng, Tam, 2. Watch the backend log: 3 engine switches, one paper at a time. Fix: jobs for the loaded engine run first, up to the per-engine limit; a waiting job can be skipped at most 4 times. | Major | High | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-002 | Dev / Local | Answer Sheets / Bulk Upload | A bulk upload ran as one job that looped over every sheet, and a global sheet lock made sheets run one at a time even with free GPU slots. Steps: 1. Bulk-upload 40 answer sheets, 2. Only 1 sheet is read at a time. Fix: one job per sheet and a lock per sheet instead of the global lock. | Major | High | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-003 | Dev / Local | Student Identification | With parallel jobs, two sheets read at the same time could both be auto-assigned to the same student. Steps: 1. Set INTERNVL_PARALLEL_JOBS=2, 2. Bulk-upload two sheets with the same roll number, 3. Both get assigned to that student. Fix: re-check under an exam lock whether the student already has a sheet; if so, hold the sheet for the teacher. | Critical | High | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-004 | Dev / Local | Evaluation / Exam Status | When sheets were graded in parallel, the first one to finish set the exam to REVIEW_REQUIRED while others were still grading. Steps: 1. Grade 2+ sheets in parallel, 2. The exam shows Review Required before grading has finished. Fix: only the last sheet still grading moves the exam to REVIEW_REQUIRED. | Major | Medium | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-005 | Dev / Local | Evaluation | Re-grading one question while a full grading run was in progress on the same sheet could run both at once and overwrite marks. Steps: 1. Start Run Evaluation on a sheet, 2. Re-evaluate one question while it is still running. Fix: one grading run per sheet at a time. | Major | Medium | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-006 | Dev / Local | OCR Pipeline | Reprocessing a question paper re-maps the exam's answer keys and sheets; in parallel this could clash with an answer sheet being saved for the same exam. Steps: 1. Reprocess the question paper, 2. While it runs, have an answer sheet of the same exam finish reading. Fix: the record-building step runs one document at a time per exam; page reading stays parallel. | Major | Medium | Claude Code | Goku | Fixed - Pending Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-007 | Dev / Local | IndicOCR Service | The service read one page at a time, so parallel Tamil jobs waited in line. Changed to read pages in parallel on the one loaded model. RISK: IndicOCR does not document that this is safe; it could crash or mix up text between pages. Steps to retest: 1. Read the same Tamil sheets with INDIC_PARALLEL_JOBS=1 and then 2, 2. Compare the text, 3. Watch nvidia-smi for out-of-memory errors. | Critical | High | Claude Code | Goku | Ready for Retest | 2026-10-26 | — | 632008a + uncommitted changes
BUG-008 | Remote Server | Ollama / Config | Parallel InternVL jobs give no speed-up unless OLLAMA_NUM_PARALLEL is set on the Ollama machine. Steps: 1. Set INTERNVL_PARALLEL_JOBS=2 in backend/.env, 2. Leave OLLAMA_NUM_PARALLEL unset on the remote server, 3. Pages are still answered one at a time. Fix: set OLLAMA_NUM_PARALLEL=2 on the remote server and restart Ollama. | Minor | High | Claude Code | Goku | Open | 2026-10-27 | — | Ollama config (no code change)
BUG-009 | Dev / Local | Licensing / IndicOCR | The IndicOCR licence needs written approval from Bodhan AI to offer it as a hosted service to other organisations, unless the provider is a nonprofit, government or academic body. Steps: 1. Read the Indic Open Model License, 2. Check it against plans to deploy ADEM for other schools. | Major | Medium | Claude Code | Goku | Open | — | — | 632008a